## Sheet1
Responsibility Matrix
Task | Rafael de Oliveira | Chang Sun | Qiran Ying | Matthew Raporte | Jianing He | Nicholas Gennuso | Completed
Vision |  | ✔ |  | ✔ |  |  | ✔
Business Rules | ✔ |  |  | ✔ |  |  | ✔
Supplementary Specification |  |  |  |  | ✔ |  | ✔
Glossary |  |  | ✔ |  |  |  | ✔
Fully Dressed Use Cases |  |  | ✔ |  |  | ✔ | ✔
Brief Use Cases | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔
Responsibility Matrix | ✔ | [5 empty] | ✔
Work Breakdown Structure | [5 empty] | ✔ | ✔
Presentation Slides | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
WBS for SG Technologies
Name | Duration | Start_Date | Finish_Date
POS System | 52 days | September 1, 2015 8:00 AM | November 11, 2015 5:00 PM
Inception Phase | 6 days | September 1, 2015 8:00 AM | September 8, 2015 5:00 PM
Vision | 1 day | September 8, 2015 8:00 AM | September 8, 2015 5:00 PM
Use Cases | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Process Sale (fully dressed) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Process Rental (fully dressed) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Process Return (brief) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
User Management (brief) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
System startup/shutdown (brief) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Credit in account (brief) | 3 days? | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Supplementary Specifications | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Glossary | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Business Rules | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
RM | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
WBS | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Deliverable - Group Submission #1 | 3 days | September 4, 2015 8:00 AM | September 8, 2015 5:00 PM
Phase 2 | 14 days | September 9, 2015 8:00 AM | September 28, 2015 5:00 PM
POS Prototype of Process Sale | 10 days | September 9, 2015 8:00 AM | September 22, 2015 5:00 PM
Software architechture document | 5 days | September 14, 2015 8:00 AM | September 18, 2015 5:00 PM
Presentation slides | 3 days | September 24, 2015 8:00 AM | September 28, 2015 5:00 PM
Update WBS/RM | 1 day | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Deliverable - Group Submission #2 | 1 day | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Phase 3 | 21 days | September 28, 2015 8:00 AM | October 26, 2015 5:00 PM
Alpha-release | 1 day? | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Design Patterns | 1 day? | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Testing | 1 day? | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Presentation slides | 1 day | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM
Update WBS/RM | 1 day? | September 28, 2015 8:00 AM | September 28, 2015 5:00 PM
Deliverable - Group Submission #3 | 3 days | October 22, 2015 8:00 AM | October 26, 2015 5:00 PM
Phase 4 | 13 days | October 26, 2015 8:00 AM | November 11, 2015 5:00 PM
Beta-release | 1 day? | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM
Developer manual | 1 day? | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM
User manual | 1 day? | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM
Experience-sharing slides | 1 day? | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM
Update WBS/RM | 1 day? | October 26, 2015 8:00 AM | October 26, 2015 5:00 PM